}

Guía1. Definición Proyecto APT

Asignatura Capstone

- PARTE I

1. Antecedentes Personales

A continuación, se presenta una tabla en la que debes completar la información solicitada.

| Nombre estudiante 1 | Lucas Alonso Olea Cornejo |
| --- | --- |
| Rut 1 | 21.609.077-2 |
| Nombre estudiante 2 | Rodrigo Riquelme |
| Rut 2 | 21.160.922-2 |
| Nombre estudiante 3 | Marco Antonio Robles Garrido |
| Rut 3 | 20.844.787-4 |
| Nombre estudiante 4 | Rodrigo Soto |
| Rut 4 | 21.067.312-1 |
| Carrera | Ingeniería en informática |
| Sede | Plaza norte |

2. Descripción Proyecto APT

En la descripción debes señalar brevemente el nombre de tu proyecto APT y las competencias del perfil de egreso que vas a poner en práctica. Si en tu carrera están definidas las áreas de desempeño, también menciona a qué áreas de desempeño está vinculado el proyecto.

| Nombre del proyecto | RollerApp |
| --- | --- |
| Área (s) de desempeño(s) | Software development (web and mobile), database and sever management, systems architecture and integration, and Quality Assurance (QA). |
| Competencias | - Develop a software solution using techniques that systematize the development and maintenance process, ensuring the achievement of objectives: Construction and integration of the responsive web frontend, the mobile application for clients, and the centralized REST API, connected to the Webpay Plus payment Gateway and deployed to the cloud - Build data models to support organizational requirements according to a defined and scalable design: Design, normalization, and implementation of the relational database model to ensure the consistency of users, catalog, quotes, orders, and concurrent transactions. - Manage IT projects, offering alternatives for decision-making according to organizational requirements: Planning, estimation, and control of the development cycle through the agile Scrum framework, managing the prioritized Product Backlog and committed deliverables over 19 weeks. - Perform certification testing of products and processes using industry best practices: Design and execution of the unit, integration, functional, and API security testing matrix, along with the systematic management of defects and re-testing. |

3. Fundamentación Proyecto APT

| Relevancia del proyecto APT | In the custom blinds and solar protection systems industry, TopRoller faces critical bottlenecks due to a service model reliant on manual WhatsApp messaging and a purely informational web portal. This scheme causes delays in quote delivery, inconsistencies in price-per-square-meter calculations, lack of coordination in scheduling technical visits, and a lack of traceability in manual bank transfer payments. The development of RollerApp is highly relevant to the computer engineering field, as it addresses the comprehensive digitization of a real business model in the Metropolitan Region. It solves a common problem in custom manufacturing companies: the need to integrate dynamic quoting engines, autonomous real-time scheduling, and transactional payment gateways under secure and scalable multi-platform architectures. |
| --- | --- |
| Descripción del Proyecto APT | RollerApp is a multi-platform software ecosystem designed to automate TopRoller's commercial and operational cycle. The solution integrates: - Responsive Web Portal and Mobile Application: Direct channels for clients to consult the interactive fabric/model catalog, calculate exact quotes based on dimensions, book technical visits (rectification/installation), and make secure electronic payments using debit or credit cards via Webpay Plus. - Backend and Centralized REST API: A normalized model that ensures the persistence, consistency, and concurrency of clients, orders, schedules, and transactions. - Administrative Portal: A centralized panel for the administration to monitor order statuses, assign crews to the technical schedule, and audit payments and commissions in real-time. |
| Pertinencia del proyecto con el perfil de egreso | The project directly articulates and consolidates the four key competencies of the degree's graduate profile: - Software development and implementation: Frontend construction (Web and Mobile), REST API development, payment gateway integration, and continuous cloud deployment. - Data model construction: Design and normalization of the relational database to support concurrent operations and transactional traceability. - IT project management: Planning and control of the software lifecycle using the Agile Scrum framework throughout a 19-week schedule. - Quality testing and certification: Design and execution of a unit, integration, functional, and endpoint security testing plan, managing defects through correction and re-testing cycles. |
| Relación con los intereses profesionales | Lucas Olea: Highly interested in Full Stack and mobile app development. Working on a project that encompasses both worlds and processes real payments will be highly beneficial for my professional future. Marco Robles: This project aligns primarily with my interests in full-stack development (web and mobile) and platform integration. It helps me develop competencies in handling payment gateways, robust authentication, and security protocols, while applying my knowledge to solve real business problems and optimize user experience. |
| Factibilidad de desarrollo del Proyecto APT | The project is entirely feasible to complete within the academic period considering the following factors: - Timeframe and Methodology: Structured over 19 weeks divided into 3 phases using the Scrum framework, allowing for short iterations and continuous delivery of tested functional increments. - Technological and Material Resources: Employs consolidated open-source technologies, design tools (Figma), API testing environments (Postman), relational database managers, and Transbank's official testing environments, operating on standard development computers and Cloud infrastructure. - Multidisciplinary Team: 4 members with a clear division of roles. |

- PARTE II

4. Objetives

| Objetivo general | Develop and implement RollerApp, a digital ecosystem composed of a responsive web platform and a mobile application connected to a centralized backend and relational database, to digitize and end-to-end automate TopRoller's curtain sales cycle. This will allow clients to request custom real-time quotes, schedule technical rectification/installation visits, and process secure electronic payments with Webpay Plus, eliminating operational dependence on manual WhatsApp channels. |
| --- | --- |
| Objetivos específicos | - Design the software architecture, the entity-relationship model of the relational database, and interface prototypes (UX/UI) for the web portal, mobile app, and administrative panel. - Program the centralized backend and REST API to manage role-based access control and authentication, the product/service catalog, the dynamic quoting engine, and reservations. - Build the responsive web portal for clients and the administration panel for centralized order management, crew assignment to the technical schedule, and business indicator visualization. - Develop the mobile application for clients, integrating catalog consultation, the dynamic dimensional quoting tool, technical visit scheduling, and secure communication with the REST API. - Integrate the Webpay Plus (Transbank) payment gateway into both the web and mobile apps, ensuring a secure transaction flow, return token validation, and automatic order confirmation. - Execute a comprehensive Software Testing plan, registering and correcting defects to ensure the quality and stability of the solution. - Deploy the system components (Web, App, Backend, and DB) to cloud infrastructure, creating user manuals and technical documentation required for the final delivery. |

5. Metodology

Descripción de la Metodología

Working Methodology: Agile Scrum Framework For the development of the RollerApp project, the Agile Scrum framework will be adopted, enabling iterative and incremental software construction through defined development cycles (Sprints). This methodology ensures the continuous delivery of valuable functional increments, rapid adaptation to changing requirements, and progressive module validation alongside the TopRoller company. Phase and Cycle Structure: The 19-week work plan is organized into three major macro-stages that frame the Sprint execution: - Phase 1: Discovery, Architecture, and Sprint 0 (Weeks 1 to 4): Client requirement gathering and analysis, creation of the relational database model and software architecture (REST API), UX/UI prototyping in Figma, and construction of the initial prioritized Product Backlog. - Phase 2: Construction and Incremental Integration Sprints (Weeks 5 to 16): Execution of development Sprints to create the base REST API, role-based authentication, web and mobile catalog views, the dynamic quoting engine logic, interactive technical agenda, Webpay Plus integration, and the Administrative Panel with KPI Dashboard. - Phase 3: Stabilization, QA, and Deployment Sprints (Weeks 17 to 19): Execution of the comprehensive testing plan, formal defect correction, performance optimization, cloud infrastructure deployment, APK generation, and final documentation delivery. Scrum Ceremonies and Artifacts: - Artifacts: Product Backlog (prioritized list of epics and user stories), Sprint Backlog (subset of committed tasks per iteration), and Product Increment (functional, tested, and potentially deployable version of the software). - Ceremonies: Sprint Planning (defining the Sprint Goal), Daily Scrum (brief 15-minute synchronization meetings), Sprint Review (practical demonstration of the increment), and Sprint Retrospective (internal performance analysis for continuous improvement). Team And Roles: - Product Owner: Responsible for defining the product vision, managing the Product Backlog, and ensuring deliverables meet TopRoller's needs. - Scrum Master: Ensures compliance with Scrum principles, facilitates communication, and removes technical/methodological blockers. - Development Team: Auto-organized multidisciplinary team in charge of technical design, FullStack programming, DB management, Webpay integration, QA testing, and continuous deployment. Individual Role Definition: - Lucas Alonso Olea Cornejo: Product Owner / Fullstack Developer. - Marco Antonio Robles Garrido: Scrum Master / Database Management. - Rodrigo Riquelme: Quality Assurance (QA) and Testing Lead. - Rodrigo Soto: Technical Design, Architecture, and UI/UX.

6. Evidences

| Evidence Type | Evidence Name | Description | Justification |
| --- | --- | --- | --- |
| Progress | Initial Project Documentation | Delivery of the project charter, functional/non-functional requirements matrix, and system scope definition. | Establishes the technical and functional foundations of the project, ensuring goal alignment and mitigating risks. |
| Final | Solution Web Page | Web platform deployed and operational for curtain sales and service scheduling, with Backend/APIs integrated, code repositories, and software testing reports | Validates the complete implementation of the web channel, demonstrating proper client-server integration and operational stability of main modules. |
| Final | Mobile Application | Functional mobile application for user service management and purchasing, including QA testing reports for the app. | Guarantees mobile accessibility and omnichannel solution capabilities, verifying correct performance on mobile devices and central database synchronization. |

Work Plan

| Plan de Trabajo Proyecto APT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Competency | Activity/Task Name | Task Description | Resources | Duration | Responsible | Observations |
| Project Mgmt & Agile | Gathering and Definition | Creation of the project charter, scope definition, gathering and specification of functional/non-functional requirements. | Google Docs, coordination meetings, PCs. | 2 Weeks (W1 - W2) | Lucas Olea Rodrigo Soto Rodrigo Riquelme Marco Robles | Facilitator: Clarity in the business model. Difficulty: Correctly defining the scope to avoid technical overload |
| Design & Architecture | Architecture and UI/UX Design | Creation of the relational database model, component architecture diagram, and high-fidelity interactive prototypes for web and mobile. | Figma, Draw.io, PCs, Internet. | 3 Weeks (W2 - W4) | Lucas Olea Rodrigo Riquelme | Facilitator: Use of real-time collaborative design tools. Difficulty: Adjusting reservation flows to be intuitive on both web and mobile screens. |
| Backend & Database | Backend and Database Development | Implementation of the relational DB schema, server configuration, and REST API development for authentication, catalog, and reservations. | IDEs, DB Managers | 4 Weeks (W5 - W8) | Rodrigo Soto Marco Robles | Facilitator: Previously normalized data model. Difficulty: Managing session security and database concurrency |
| Web Interfaces | Web Frontend and Admin Panel | Programming the client web portal and the administrative panel consuming the REST API | IDEs, Web Frameworks | 4 Semanas (S9 - S12) | Lucas Olea Rodrigo Soto | Facilitator: Previously approved Figma prototypes. Difficulty: Maintaining responsive design and complex global state management. |
| Mobile Apps | Mobile App Development | Construction of the mobile client app, programming interfaces, reservation flow, interactive navigation, and REST API endpoint consumption. | Mobile Frameworks | 4 Weeks (W13 - W16) | Rodrigo Riquelme Marco Robles | Facilitator: Reuse of endpoints already tested in the web phase. Difficulty: Adapting interfaces and performance across different resolutions and OS versions. |
| Systems Integration | Payment Gateway Integration | Implementation of the Webpay SDK/API (Transbank), configuration of transactional callbacks, and real-time payment confirmation. | Transbank API/SDK, test credentials, Postman, VS Code. | 3 Weeks (W15 - W17) | Lucas Olea Rodrigo Soto | Facilitator: Well-documented testing environment. Difficulty: Handling mobile app returns after payment |
| QA & Testing | Pruebas de Integración y Correcciones | Execution of functional testing plans, load/security testing, full flow verification, documentation, and bug resolution. | Postman, version control tools, unit tests. | 2 Weeks (W17 - W18) | Lucas Olea Rodrigo Riquelme Marco Robles | Facilitator: Test cases defined from initial requirements. Difficulty: Resolving data inconsistencies generated during stress testing. |
| Cloud Infrastructure | Deployment and Final Documentation | Production deployment of the API and web platform on cloud servers, generation of the mobile installer (APK). | Cloud platforms, office tools, mobile compiler | 2 Weeks (W18 - W19) | Lucas Olea Rodrigo Soto Rodrigo Riquelme Marco Robles | Facilitator: Build automation and previously versioned code. Difficulty: Configuring environment variables and SSL certificates in production. |

8. Carta Gantt

| Actividad | Fase 1 |  |  |  | Fase 2 |  |  |  |  |  |  |  |  |  |  |  | Fase 3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | S 1 | S 2 | S 3 | S 4 | S 5 | S 6 | S 7 | S 8 | S 9 | S 10 | S 11 | S 12 | S 13 | S 14 | S 15 | S 16 |  | S 17 | S 18 | S19 |
| 1. Requirements gathering, scope, and use cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Relational DB model and software architecture design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. High-fidelity UX/UI prototyping in Figma |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Repositories, development environment, and standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Database creation and auth/user endpoints |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. CRUD and endpoints for fabric, product, and service catalog |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Initial layout of Web and Mobile App catalog views |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Logic and endpoints for the dynamic quoting engine |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Interactive quoting tool implementation (Web and App) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. Order generation flow and state management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. Endpoints and schedule availability validation logic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Calendar interface for reservations (15-min lock) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. Technical visit assignment and management module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. Administrative Panel (Backoffice) development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. Transbank Webpay Plus payment gateway integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16. Transactional notification service implementation (SMTP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. Unit, integration, and functional testing execution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18. Defect correction and performance optimization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19. Cloud deployment (Render/Vercel) and APK compilation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20. UAT validation, user manuals, and final report delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |